## Debenham
Why | What | How | Data | When | Who | Cost/year (£) | Confidence | Evaluation
What is the objective of the works which are to be monitored? | What are you going to monitor | What methods are you going to use? | Add information on the baseline data you have collected (type, frequency, method used) | What periods over the year and how often? (to indicate variability) | Who is going to do this? | (Can be in kind) | High/ medium/ low robustness of monitoring | How/when/ who. Monitoring results collated and evaluated | Total number of surveys required
To monitor habitat diversity and show changes through implementation of NFM techniques on habitat and ecological status for fish, invertebrates and macrophytes. | Habitat diversity | Phase 1 habitat survey | 1 survey before work 2 surveys post works | Between May to September | partners |  | High |  | 3
| Habitat and morphological adjustment | Fixed point photography of the attenuation pond. | 1 pre works survey, 1 during works survey 2 post works survey | Pre: June, October 2018 During construction. Post construction: October 2018 onwards every 6 mths. At all NFM features | partners |  | High |  | 4
|  | Over-wintering/breeding bird surveys (species counts) | Before and after | Before, and for 2 years post works | partners |  | High |  | 3
|  | Aerial drone survey, | Before and after | Spring (prior to vegetation growth). 1 pre, 2 post | IDB? | Potential contribution in kind. Not essential monitorring | High |  | 3
|  | Topo and bathemetric surveys: Cross-sections of inflow into pond and ds outfall channel. and floodplain extent to inform 2D model | Pre-construction and as-built | 1 pre 1 post | IDB? |  | High |  | 2
Ascertain how flood risk to properties is reduced following NFM intervention(s) | Hydrometric data | Tipping Bucket Raingauge & check gauge installed nearby to the NFM interventions. | Rainfall correlated to water levels prior to construction starting | As and when rainfall occurs. Logger used to collect data as not collected to telemetry. | EA. Hydrometry and Telemetry to maintain and collect logger data. | Approx £800 | Medium | NFM project manager following flood events | NA - continuous
|  | Pressure transmitter installed upstream of the invervention, and one downstream, plus one in the pond. (3 in total) Back up data loggers. | Water levels prior to the NFM construction starting | Constant 15 minute water level recording | EA. Permanent water level installation connected to telemetry. Hydrometry and Telemetry to install, maintain and collect data. | Approx £3300 | High | NFM project manager following flood events | NA - continuous
|  | 2D modelling | Compare pre and post installation situation | Model run in 2019 post construction using water level information to refine hydraulic model | WEM consultant | Cost included in national modelling project | High | 2019 | NA
Photography | Flow pathways and performance of each of the NFM interventions. | Time lapse photography | n/a | Continuous. Installation either in advance of when flooding expected or permanent installation. | tbc | Approx £400 | Medium | NFM project manager following flood events | NA- continuous
Ascertain reduction of in-channel sediment following NFM intervention | Sediment accumulation in the storage feature | Re-survey bed level periodically when dry, in order to accurately determine rate of sedimentation | once per year | tbc | IDB? |  | High
Ascertain reduction of suspended solids removed from system | Water quality | Water samples taken during peak rainfall events | 5 events prior to NFM intervention | 5 events per year, 5 pre and 10 post intervention | EA | tbc | High | NFM project manager following flood events
Ascertain reduction of nutrients removed from system | Water quality | Water samples taken during peak rainfall events | 5 events prior to NFM intervention | 5 events per year, 5 pre and 10 post intervention | EA | tbc | High | NFM project manager following flood events
Evidence gap being addressed The effectiveness of an online storage area to mitigate flood peaks for larger flood events in a small (4km2) catchment & how quickly the sediment accumulates and maintenance requirements.
Note on C7: wtodd: Partners or IDB will be likely to require the pre construction survey information to inform the design of the features.

## 10 step plan
Monitoring
1. Surveying the bed levels, bank top levels and inflow/outflow spill levels in the new sedimentation pond once it has been excavated. Fine
2. Install a gauge board (also levelled in to Ordnance Datum) in the deepest part of new sedimentation pond and record regular/periodic manual readings taken from it, especially after each major rainfall event. Fine
3. Re-survey bed level periodically when dry, in order to accurately determine rate of sedimentation. Fine
4. Maintain accurate diary (with dates and times) of all maintenance and management operations on new the new sedimentation pond and the new ‘wet’ offline storage area. It is very important to record the date and time of all changes to inlet or outlet control levels. Fine, need landowner to assist
5. As soon as is possible install a well protected (in terms of the casing and support) water level recorder in the watercourse upstream of the entry point to the new sedimentation pond. Fine (H&T)
6. As soon as possible install a well protected water level recorder in the watercourse downstream of the exit point from the wet offline storage area. This point and point 5 allows some form of a baseline record to be generated, depending on the duration of time between now and the construction of the new features. Fine (H&T)
7. Level in all water level recorders to Ordnance Datum. Fine, (H&T)
8. Install a tipping bucket raingauge in this part of the catchment. Fine (H&T)
9. Any recorded observations and photos of the local catchment, watercourse and new ponds during more significant rainfall-runoff events would be very informative. Can help identify potential major runoff and/or sediment sources and pathways, and provide further information on the operation of the ponds during events. Fine
10. Monitoring general changes in the land use and land management in the upstream catchment over time would allow further commentary around runoff and/or sediment sources. Explore CSF links?